## Table 1
Key Results (Long Term Objectives) | Tactics (Short Term Objectives) | Responsibility (Who) | Timeline (When) | 2018 Q2 | 2018 Q3 | 2018 Q4 | 2019 Q1 | 2019 Q2 | 2019 Q3 | 2019 Q4 | 2020 Q1 | Completed | 4th Quarter Update - Jan/Feb/Mar 2020
Strategic Priority #1 – Partnerships and Collaboration
1.1 Develop Inter-Municipal Collaboration Framework
| 1.1.1 Create terms of reference for ICF group | Ken and Kyle | Q3 2018 (two weeks after receiving grant) | [8 empty] | ü
| 1.1.2 Develop and advertise RFP | Ken, Kyle, Jay and Mark | Q3 2018 (one month after receiving grant) | [8 empty] | ü
| 1.1.3 Select and review RFP applicants for interview | ICF group (Reeve, Mayor, CAOs) | Q3 2018 (3-4 weeks) | [8 empty] | ü
| 1.1.4 Interview RFP applicants and select | ICF group (Reeve, Mayor, CAOs) | Q4 2018 (2 weeks) | [8 empty] | ü
| 1.1.5 Develop contract | Sheila, Kim, Norm, Ken | Q4 2018 (1-2 weeks) | [8 empty] | ü
| 1.1.5 Consultant start up meeting with ICF group | ICF group | Q4 2018 (2 weeks) | [8 empty] | ü
| 1.1.6 Finance component for ICF (recreation, ASP, industrial park, etc.) | Mir/Darlene | Q3/Q4 2019 (1 month) | [9 empty] | ICF - Recreation Completed. ASP & Industrial Park 2021
| 1.1.7 Governance component for ICF (Bylaws, policies, etc.) | Ken/Sheila | Q2 2019 | [8 empty] | ü
| 1.1.9 Consultant to complete ICF | Consultant/ICF group | Q4 2019 (Must be complete by April 2020) | [8 empty] | ü
| 1.1.10 IDP | ISL | Spring 2019 | [8 empty] | ü
| 1.1.11 Recreation Study | Sheila, Ken, Norm, Kim | Spring 2019 | [8 empty] | ü
1.2 Build relationships with both neighbor Indigenous communities
| 1.2.1 Cross cultural/indigenous relations training | - Ken plus one member of the management team | Q4 2018 | [9 empty] | County will reschedule
|  | - 2 management team members | Q4 2019 | [9 empty] | Waiting on County to schedule
| 1.2.2 Connect with Rudy Parenteau (AEMA) as relationship builder | Paul | Q2 2018 | [9 empty] | Ongoing
| 1.2.3 Plan first meeting with Frog Lake to begin relationship building | County Reeve, Town Mayors, Ken, Sheila, Paul, Laverne Wilson, Rudy Parenteau | Q4 2018 | [9 empty] | Jan 16 cancelled due to weather
| 1.2.4 Regular meetings with Frog Lake to discuss fire, | County Reeve, Town Mayors, Ken, | [10 empty] | 2020/2021
| doctors, hospital, health and safety, emergency | Sheila, Paul, Laverne Wilson, Rudy | 2019 – 2021 | [9 empty] | 2020/2021
| management, RCMP, water, road | Parenteau | [10 empty] | 2020/2021
| 1.2.5 Develop fire agreement with Frog Lake | County | Q4 2021 | [9 empty] | County responsible for.
| 1.2.6 Grand opening of Fishing Lake administration building | Mayor, Council, Ken, | Q2 2018 (June 19) | [8 empty] | ü | Attended
| 1.2. 7 Plan first meeting with Fishing Lake to begin relationship building | County Reeve, Town Mayors, Ken, Sheila, Paul, Laverne Wilson, Rudy Parenteau | Q4 2018 | [9 empty] | Waiting on Fishing Lake
| 1.2.8 Regular meetings with Fishing Lake to discuss fire, | County Reeve, Town Mayors, Ken, | [10 empty] | 2020
| doctors, hospital, health and safety, emergency | Sheila, Paul, Laverne Wilson, Rudy | 2019 – 2021 | [9 empty] | 2020
| management, RCMP, water | Parenteau | [10 empty] | 2020
| 1.2.9 Update fire agreement with Fishing Lake | County Reeve, Town Mayors, Ken, Sheila, Paul | Q4 2019 | [8 empty] | ü | County Completed
| 1.2.10 Plan first meeting with Onion Lake to begin relationship building | County Reeve, Town Mayors, Ken, Sheila, Paul, Laverne Wilson, Rudy Parenteau | Q4 2018 | [9 empty] | 2020/2021
| 1.2.4 Regular meetings with Onion Lake to discuss fire, | County Reeve, Town Mayors, Ken, | [10 empty] | 2020/2021
| doctors, hospital, health and safety, emergency | Sheila, Paul, Laverne Wilson, Rudy | 2019 – 2021 | [9 empty] | 2020/2021
| management, RCMP, water | Parenteau | [10 empty] | 2020/2021
1.3 Meet with County of St. Paul semi-annually
| 1.3.1 Plan and organize first meeting with County of St. Paul – first meeting to take place in November | Ken to contact Sheila | [9 empty] | ü | Waiting on COVID-19
| 1.3.2 Semi-annual meetings with County to discuss fire, FCSS, recreation, water, roads, economic development. Use collaborative process to draft agenda one month prior to meetings. | Town of Elk Point (Mayor, Council, Ken) County of St. Paul (Reeve, Council, Sheila) | November/May 2018 – 2021 | [8 empty] | ü
| 1.3.3 Annual meeting with Town of St. Paul to discuss recreation, fire, water | Ken to contact Kim | Q2 2018 (Set meeting date by July) | [9 empty] | 2020
| 1.3.4 CAOs of County, Town and Summer Village to meet every 2 months | Ken | Ongoing | [9 empty] | Ongoing
| 1.3.5 Joint application with Horseshoe Bay for internship | Ken | Q4 2018 | [9 empty] | SVHB Declined
Strategic Priority #2 - Fiscally Responsible
2.1 Look for efficiencies in shared services/ resources
| 2.1.1 Truck Fill - Grand opening event with County and Province | Council, County, CAOs, Jay | Q3 2018 | [9 empty] | No Grand Opening - County not interested
| 2.1.2 Continue with gravel | Jay | Ongoing | [9 empty] | Ongoing
2.1.3 Airport improvement project approved - $491,000
| -Committee to approve design | Airport Committee - Mayor, Jay, Council, Ken, Mir | Q2 2018 - June 15 | [8 empty] | ü
| -Engineers to complete tender and RFP | Engineers | Q3 2018 - July 1 | [8 empty] | ü
| -Review and approve tender and RFP | Airport Committee | Q3 2018 - July 15 | [8 empty] | ü
| -Market RFP | Airport Committee | Q3 2018 - August 15 | [8 empty] | ü
| -Pre-Qual: Review companies for safety program | Paul | Q3 2018 - August 30 | [8 empty] | ü
| -Engineer to present and recommend proponent | Airport Committee | Q3 2018 - September 15 | [8 empty] | ü
| -Select proponent and begin work | Airport Committee | Q3 2018 - September 30 | [8 empty] | ü
| -Mir to provide financial report beginning, middle and end of project | Mir | Q3 2018 (October 1), Q1 2019 (January 15), Q2 2019 (June 20) | [9 empty] | June 2020.
| -Project completion | Airport Committee | Q4 2019 | [8 empty] | ü
| -Engineers to train County staff on maintenance | Airport Committee | Q4 2018 | [8 empty] | ü
2.1.4 Transfer Station
| - Develop tracking documentation for salt and sand usage | Jay, Ken, Sheila and Mark | Q3 2018 | [9 empty] | Jay is working on it
| - Review usage documents in preparation for budget | Jay and Ken | Q2 2019 | [8 empty] | ü
| - Investigate machine for Pit | Jay, Ken and Sheila | Q3 2018 | [8 empty] | ü | Shamrock equipment on site
2.1.5 Regional Line
| - Check agreements annually | Jay/Ken | Q4 2018, 19, 20, 21 | [8 empty] | ü
| - Water commission to send letter to ISL | Ken | Q2 2018 (May) | [8 empty] | ü
| - Determine if contractor is needed to fix leaks | Jay | Q2 2018 (June) | [8 empty] | ü
2.1.6 Water Treatment Plant
| - Plant tour | Mayor, Council, Ken, Commission Board, Jay, Paul, Sheila, Bryan, Burt | Q3 2018 (August 23) | [8 empty] | ü
| - Review agreement | Ken | Q1 2020 | [8 empty] | ü
2.1.7 FCSS
| - Review montly report | Council, Ken, Janice | Ongoing | [9 empty] | Ongoing
| - Review agreement | Ken, Sheila | Q1 2020 | [8 empty] | ü
2.1.8 Emergency Services
| - Review agreeement annually | Paul | Q4 2018, 19, 20, 21 | [9 empty] | Ongoing
| - Follow schedule of mutual aid and Memorandum of Understanding | Paul | [9 empty] | ü
| - CORE status certificate audit - review recommendations and implement | Paul | Q3 2018 | [8 empty] | ü | Passed - Two Ongoing Reviews
2.1.9 Fire
| - Monitor and develop agreements with indigenous communities and County | Paul, Ken, Council | Q4 2019, 20, 21 | [9 empty] | Ongoing - County working on
| - Recruitment of volunteers | Fire Chief | Ongoing | [9 empty] | Ongoing
| - Training in St. Paul | Fire Chief | Ongoing | [9 empty] | Ongoing
| - Regional Deputy Chief - recruitment, evaluation | Fire Chiefs of Town of St Paul, County of St Paul, Town of Elk Point, Sheila, Tim, Ken | Q3 2018 - Q1 2019 | [8 empty] | ü
2.2 Continue asset management
| 2.2.1 Add new equipment to asset management plan | Jay | Q2 2018 | [8 empty] | ü
| 2.2.2 Continue asset management plan | Jay | Ongoing | [9 empty] | Jay
2.3 Strengthen partnerships
| 2.3.1 Research other communities resource grant writing, hire on as needed basis, and negotiate rates | Ken | Q4 2018 | [8 empty] | ü | Using MPE Engineering - Grant writer and ISL Engineering
| 2.3.2 Maintain relations with Nikifouruk | Ken/Jay | Ongoing | [8 empty] | ü | Ongoing
Strategic Priority #3 - Safe and Healthy Community
3.1 Bylaw enforcement position
| 3.1.1 Complete hiring process - check references and animal control contract, develop & advertise job description | Council, Ken | Q2 2018 | [8 empty] | ü
| 3.1.2 Contractor beginning July 1 | Council/Ken | Q2 2018 | [8 empty] | ü
| - Develop and implement communication plan with a focus on public education | Enforcement Contractor | Q3 2018 (July-Sept) | [8 empty] | ü
| - Start enforcement | Enforcement Contractor | Q3/Q4 2018 (Oct-Dec) | [8 empty] | ü
| 3.1.3 Review effectiveness of contract and extend to one year (review annually) | Ken | Q4 2018 | [8 empty] | ü
| 3.1.4 Add CPO position | Ken/Council | Q4 2019 | [9 empty] | Not proceeding due to budget constraints
| 3.1.5 Update Bylaws | Krysten/Ken | Q4 2020 | [8 empty] | ü
3.2 Support and advocate for RCMP
| 3.2.1 Support satellite detachment application for Fishing Lake | Ken | Q3 2018 | [8 empty] | ü
| - send letters from Mayor, Council, Chamber President, Reeve and Council from County, MLA, non-profit organizations, industry, CNRL, BUMP, etc. | Ken | Q3 2018 | [8 empty] | ü
| 3.2.2 Semi-annual meeting with MLA and MP | Ken | Q3 2018 | [8 empty] | ü | MP/MLA
| 3.2.3 Add this to agenda item for joint Council meeting | Ken | Q3 2018 | [8 empty] | ü | 2019 Fall - County to host
| 3.2.4 Grand opening of new detachment | [11 empty] | Waiting on COVID-19
| - Planning | Sgt. Henry, Ken | Q2 2018 | [9 empty] | Waiting on COVID-19
| - Event | Mayor/Council/Ken | Q3 2018 (July) | [9 empty] | Waiting on COVID-19
| 3.2.5 Develop a relocation package for RCMP tailored to specific need | Ken/Sgt. Henry | Q4 2018 | [9 empty] | Summer 2020
| 3.2.6 Investigate a shared service staff model between RCMP station and town | Ken, Detachment | Q4 2020 | [9 empty] | Budget restraints 2019 - Not interested
3.3 Support and advocate for local health care
| 3.3.1 Investigate a centralized service opportunity with massage, chiropractor, physio, etc. | Mayor, Ken | Q4 2020 | [9 empty] | Budget constraints, not proceeding at this time
| 3.3.2 Strengthen relationships with indigenous and | [10 empty] | ü
| County to make sure hospital does not close --- keep the | Mayor, Council, Ken | Ongoing | [9 empty] | Ongoing
hospital on the agenda of MLA
| 3.3.3 Develop a relocation package, play a facilitator role and advocate town attraction | Mayor, Council, Ken | Q4 2018 | [8 empty] | ü
| 3.3.4 Supporting nurses and union – make sure it is on agenda with MLA and MPs (Mayor and Council, along with Reeve and Council) | Mayor and Council, along with Reeve and Council | Ongoing | [8 empty] | ü
| 3.3.5 Prairie EMS are not meeting requirements - Joint County/Town letter has been sent to AHS | Town, County, Sheila, Ken | Q2 2018 | [8 empty] | ü | Waiting on government - County sent letter
| 3.3.6 Medical assist calls need to be redirected - fire chief needs to be educated on what they will respond to | Fire Department | Q2 2019 | [9 empty] | COVID-19 - One Call in 2 Months
Strategic Priority #4 - Business Opportunities
4.1 Look into an alternative business model to attract large industry
| 4.1.1 Continue supporting site selection process (rail, natural gas, power, pave Highway 41) | Council, Ken, Administration | Q2 2018 | [9 empty] | Ongoing
| 4.1.2 Design organizational structure to support large industry attraction | Ken | [10 empty] | Budget contraints
| - Remove Bylaw Officer duties from CAO | Council, Ken | Q3 2018 | [8 empty] | ü
| - budget for external consultant to assess organization | [11 empty] | EDC reviewed - recommend status quo
| need (Council to approve). Nichols Applied Mgmt | Council, Ken | Q3 2018
conducting this.
| Investigate opportunities for future administration buildings | Mayor, Ken | Q3 2018 | [8 empty] | ü | Budget constraints. Developer and Builder interested. Need private commitment.
| - Use collaborative process and staff engagement to develop new structure | Ken, Administration | Q1 2019 | [8 empty] | ü
4.2 Support downtown revitalization and beautification
4.2.1 Clean up vacant buildings
| - Encourage grassroots support - involve the Chamber (Mayor to discuss with Chamber President) | Mayor/Chamber | Q3 2018 | [9 empty] | Bylaw Officer/PW's working on list as time and funding allow
4.2.2 Business revitalization plan
| - Policy/plan for incentives – develop draft with Chamber | Council/Chamber/Ken | Q2 2019-Q3 2020 | [8 empty] | ü
| - Apply for grant (CARES program) | Ken | Q4 2019 | [8 empty] | ü
| - Hire consultant for revitalization plan 2019 – 2020 (consultant to engage hub, non-profit groups, County, indigenous) | Ken | Q1 2020 | [9 empty] | Budget for 2020
| - Banners for highway (directional and attractive) - joint partnership with County | Ken | Q4 2018 | [8 empty] | ü
| - Talk to Atco Electric about sponsoring utility box wraps | Ken | Q3 2020 | [9 empty] | Budget for 2020
4.2.3 Gateway Entrance
| - Trees (Memorial Project) Boulevard Hwy 41 | Jay | Q1 2020 | [9 empty] | Cut due to budget constraints
| - Sign (Recognition) | Jay | Q2 2020 | [9 empty] | Cut due to budget constraints
Strategic Priority #5 - Resident Communication and Engagement
5.1 Pass public participation policy
| 5.1.1 Draft public participation policy | Ken | Q2 2018 | [8 empty] | ü
5.2 Modernize website
| 5.2.1 As soon as decision is made by County on the provider, communications intern to develop, redesign, and explore the use of social media | Ken, Mir, Crystal, Jay | Q4 2019 | [9 empty] | Octopus Creative - 1st draft completed
5.3 Investigate how the community wants to be engaged
| 5.3.1 Utilize multiple events to reach out to community | Mayor, Council | Q2 2018
| - Pancake Breakfast (name badges, t-shirts) | [10 empty] | ü
| -BBQ | [10 empty] | ü
| -Information Night | Recreation Coordinator | Q3 2018 | [8 empty] | ü
| -Public Works Employees | Public Works Employees | Ongoing | [9 empty] | Ongoing